## Slide 1
Access & Privacy Section
Stabilization and Modernization
Progress, current state and modernization priorities
October 6, 2026
Notes: SPEAKING NOTES
Chair and Commissioners, our handling of access and privacy requests has fallen short of the service people should expect from us. The resulting backlog has damaged the confidence of this Commission and the Privacy Commissioner. We accept responsibility for allowing the Section to reach this position. People waiting for information deserve a service they can rely on. We owe them, and you, an honest account of what went wrong and evidence that our response is improving the service people receive. And while we recognize that our historical handling of access requests has undermined confidence, we are resolutely addressing that failure and focused on earning back trust.
Today, we will explain the scale of the work, the changes we have introduced, and the results we can substantiate. This presentation covers improvement and modernization of the Access and Privacy Section.
I want to set expectations clearly at the outset. We cannot fix this overnight or quickly. At the same time, the length of the recovery cannot become an excuse for delay. You should expect us to demonstrate progress along the way and be candid about what remains difficult.
The confidence we are asking you to develop must come from performance over time. We understand that assurances alone will not restore trust.

## Slide 2
Why stabilization was required
Sustained demand and constrained capacity created material operational pressure.
4,000
Estimated backlog as of May 2026
Up to 2000
Requests not yet entered into the system
2,000
Unassigned files in Gatekeeper
6
Vacancies in the Section as of May 31, 2026
Review findings
Increasing demand and limited specialized capacity
Inconsistent roles, workflows and decision-making
Lengthy training requirements and limited cross-training
Growing privacy-management responsibilities
Executive implication
The Section needed to stabilize capacity while simultaneously reducing legacy work and strengthening privacy services.
Notes: SPEAKING NOTES
The May 2026 estimate put the backlog at approximately 4,000 files. The slide also identifies up to 2,000 requests not yet entered into the system and 2,000 unassigned files in Gatekeeper. These figures describe a serious loss of control over the flow of work.
For a person waiting for a response, an unentered or unassigned request means further uncertainty. It also makes it harder for management to establish a reliable picture of what needs attention and how to prioritize it.
The review identified inconsistent roles and workflows, lengthy training requirements, and limited cross-training. There were six vacancies in the Section as of May 31, alongside increasing demand and growing privacy-management responsibilities.
These conditions help explain how the problem developed. They do not excuse the outcome. Our responsibility is to put the Section in a position to meet its obligations reliably.
We have to address accumulated work while continuing to handle incoming requests and strengthening privacy services. That is why the response has to reach beyond a short burst of extra effort. The way we assign work, develop staff and make decisions also has to improve.
TRANSITION
The next slide shows the concrete changes introduced since June.

## Slide 3
From assessment to implementation
Actions introduced since June 2026 span workforce, workflow, quality and technology.
Workforce
Six vacancies filled
Expanded training across file types
Flexible work and broader overtime access
Workflow
File-assignment targets
Closure blitzes and workload tracking
Broader intake screening and prioritization
Quality & Ownership
Risk-based QA authority
Analysts lead OIPC review responses
Complex and high-risk files retain secondary review
Technology & Privacy
Improved Gatekeeper functionality
New intake and file-tracking forms
Expanded PIA support and privacy advisory work
Axon video redaction
Notes: SPEAKING NOTES
Since June, the response has addressed workforce capacity, workflow, quality and technology together.
The Section filled six vacancies, expanded training across file types, and broadened access to flexible work and overtime. Filling positions matters, but people also need time and support to become effective across different types of files. Overtime can support recovery, but we should not build a permanent service around exceptional effort.
On workflow, the team introduced file-assignment targets, closure blitzes and workload tracking, alongside broader intake screening and prioritization. In addition, we have worked with HR to repurpose an existing FTE from PSS to move into Legal to assist with all legal requests for records, which typically are very time sensitive but do not require the level of detailed analysis as an access request under ATIA. These changes give the team a more structured way to manage the work.
We have also changed how responsibility and review operate. Some analysts now lead responses to OIPC reviews, with risk-based quality-assurance authority to reduce the number of redactions for disclosures to agencies with statutory authority to compel our disclosure of info, and secondary review retained for complex and high-risk files. That safeguard matters. Improving speed must not come at the expense of sound disclosure decisions or privacy protection.
The team has improved Gatekeeper functionality, introduced intake and tracking forms, and expanded privacy impact assessment support and advisory work. The adoption of Axon video redaction technology has cut down the time required to process BWC and ICV video by at least 30%.
These changes respond to the weaknesses identified in the review. Filling vacancies and expanding training strengthen capacity. Assignment targets and workload tracking improve oversight. Changes to review authority support more efficient decisions, while secondary review remains in place for complex and high-risk files. They are changes we can point to, while recognizing that their lasting value depends on the results they produce.
TRANSITION
We are beginning to see that additional capacity in closure volumes.

## Slide 4
Early results show increased processing capacity
Closure volumes rose sharply in Q3, but the gains must be sustained.
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct est. | Nov est. | Dec est.
Monthly closures | 203 | 114 | 227 | 243 | 125 | 222 | 431 | 338 | 438 | 400 | 400 | 400
113%
Increase in average monthly closures: Q3 vs. Jan–Jun
2,341
Year-to-date closures through September
3,541
Estimated 2026 closures, including Q4 projection
Notes: SPEAKING NOTES
This is an encouraging early signal. Average monthly closures in the third quarter increased by 113 per cent compared with January through June. The team closed 2,341 files through September. That improvement deserves recognition, particularly given the scale of the work still ahead.
But we need to be precise about what these results show. They demonstrate increased processing capacity over this period. Closure volumes alone do not tell us whether incoming demand is outpacing our work or whether people are receiving timely responses.
The year-end figure of 3,541 closures includes a projection of 400 closures in each of October, November and December. Those projected closures are not completed work. We should treat the projection as an expectation to test against actual performance.
The next test is whether the team can sustain the improvement while managing new requests and maintaining quality. We should also look at the age of the remaining files, so that stronger closure numbers do not obscure people who have waited the longest.
I would ask the you to take measured encouragement from these results. The team has demonstrated that processing capacity can improve, but people are still waiting for information and they need to experience that improvement themselves. Our responsibility is to sustain the gains and demonstrate better timeliness alongside sound decisions.
TRANSITION
The next slide makes clear why we are not yet where we need to be.

## Slide 5
Progress is real, but material risk remains
Backlog, timeliness and increasing complexity require continued executive attention.
3,500
Verified backlog as of September 30, 2026
23%
Q3 files closed within 60 weekdays
≈50%
Q3 closures requiring more than 120 business days
Key risks
Legacy files competing with new statutory requests
Growing privacy-review and advisory demand
Increasing disclosure and information-sharing complexity
Remaining Director and Manager recruitment
Mitigation focus
Prioritization and complexity-based triage
Focused backlog reduction and workload reviews
Staff development, guidance and standardized practices
Clear metrics, monitoring and regular reporting
Notes: SPEAKING NOTES
The verified backlog stood at 3,500 files on September 30. Only 23 per cent of third-quarter closures were within 60 weekdays, and approximately half required more than 120 business days. Those figures are a sobering reminder of the delays people continue to experience.
This is why we cannot responsibly offer a quick resolution. Legacy files compete with new statutory requests, while privacy-review demand and disclosure complexity continue to create pressure. Director and Manager recruitment also remains outstanding in this update.
The mitigation focus includes complexity-based triage, focused backlog reduction and workload reviews. Staff development and standardized practices support that work, together with clear monitoring and regular reporting.
We should be judged on whether these measures improve timeliness as well as reduce the backlog. That means showing you what is happening to older files and explaining material setbacks, rather than relying on an overall closure total.
The seriousness of the remaining position does not erase the team's progress. It does mean we must sustain that progress before asking you to regard the service as recovered.
TRANSITION
The roadmap sets out the longer-term work needed to make improvement last.

## Slide 6
Improvement roadmap and executive focus
Sustain current gains while building a durable access and privacy program.
2026–2027
2027–2028
Transform intake, triage and workload management
Create structured training, readiness measures and knowledge resources
Modernize SOPs, templates and governance
Evaluate compliant AI support and strengthen dashboards
Build supervisory and management capacity
Reduce dependence on overtime and crisis-response initiatives
Strengthen privacy-management and breach-response readiness
Establish metrics-driven continuous improvement
Executive focus: backlog reduction • timeliness • quality • workforce readiness • modernization milestones
Notes: SPEAKING NOTES
The roadmap extends across 2026–2027 and 2027–2028. That reflects the sustained work required to build a service we can rely on. It should not mean waiting until the end of the roadmap to see results.
The first phase focuses on intake and workload management, structured training, and updated procedures and governance. It also includes stronger dashboards and evaluating compliant AI support. AI is an option to assess carefully, not an assumed solution or a guaranteed source of productivity.
The later phase focuses on supervisory and management capacity and reducing dependence on overtime and crisis-response initiatives. It also strengthens privacy management and breach-response readiness, with continuous improvement guided by metrics.
We welcome the Commission's scrutiny of our progress. We will distinguish completed improvements from work still underway and be candid about setbacks. The areas for continued CPC scrutiny are backlog reduction, timeliness, quality, workforce readiness and modernization milestones. Our request is that you hold us to visible progress in those areas, while recognizing the sustained effort this recovery requires.
We cannot responsibly give a firm backlog-clearance date from the information presented today. A credible forecast needs reliable intake and completion trends, together with the complexity of the remaining work and available capacity.
I want to close where I began. We accept responsibility for the shortcomings that brought us here, and apologize to those affected by delays. We have changed the way the Section operates and are demonstrating stronger processing capacity. That gives us a reason for cautious optimism but there is substantial work ahead. We understand that rebuilding public trust requires sustained improvement that people can see in the service they receive. We intend to earn that trust through sustained results and honest reporting. Thank you. We welcome your questions.